UNIT 2 AGILE MINI-PROJECT

Agile Project Planning

Student Record and Academic Management Platform

| Project Information | Details |
| --- | --- |
| Project Type | Unit 2 Agile Mini-Project |
| Method | Agile / Scrum |
| Product | Student Record and Academic Management Platform |
| Focus | User Stories, Backlog, Estimation, Sprint Planning and Scrum Execution |
| Prepared By | Yash Bhor |

# Table of Contents

1. Agile Project Planning Report

2. Product Vision Document

3. Scrum Team Structure

4. Scrum Roles and Responsibilities

5. Epic Documentation

6. User Story Repository

7. Acceptance Criteria Document

8. Prioritized Product Backlog

9. Story Point Estimation Sheet

10. Sprint Planning Document

11. Sprint Backlog

12. Scrum Board

13. Burndown Chart

14. Sprint Review Report

15. Sprint Retrospective Report

16. Agile Framework Comparison Report

17. Project Timeline and Release Roadmap

18. Complete Agile Documentation Summary

# 1. Agile Project Planning Report

This document translates the software product into an Agile delivery plan. The application is divided into functional Epics, each Epic is broken into User Stories, and the stories are prioritized, estimated and organized into Sprints.

## Product Context from Unit 1

This plan builds on the Unit 1 product discovery work. Before the Agile deliverables were prepared, the following were reviewed: the Product Vision and Mission statements, the stakeholder analysis, the business requirements (BR-01 to BR-07), the functional requirements (FR-01 to FR-12), the non-functional requirements (NFR-01 to NFR-10), the three user personas (Student, Faculty Member and Academic Administrator), the MVP definition and the seven-phase Product Roadmap.

## Plan at a Glance

The platform is organized into 7 Epics and 27 User Stories totalling 111 Story Points. Delivery is planned over 4 one-week Sprints using the Scrum framework.

## Agile Objectives

Deliver useful functionality incrementally.

Prioritize work according to business value and user importance.

Use acceptance criteria to define completion.

Make progress visible through the Product Backlog and Scrum Board.

Review completed work and use feedback to improve subsequent Sprints.

## Definition of Done

Acceptance criteria are satisfied.

Implementation is integrated into the product.

Relevant tests pass.

No known critical defect remains.

The completed story can be demonstrated during Sprint Review.

# 2. Product Vision Document

Develop a secure and user-friendly Student Record and Academic Management Platform that enables educational institutions to efficiently manage student records, attendance, academic performance, course registration and reporting through a scalable web-based application.

## Agile Product Objective

Deliver the platform incrementally through short Sprints, prioritizing secure access and core academic workflows first.

## Primary Users

Students, faculty members, academic administrators, examination staff and IT support personnel.

## Business Benefits

Centralized academic information, reduced repetitive manual work, improved attendance and result visibility, consistent reporting, and controlled access to records.

## Success Criteria

Success is measured by: (1) all 27 User Stories meeting their Acceptance Criteria and the Definition of Done by the end of Sprint 4; (2) every user role limited to its permitted functions, verified by role-based access tests with zero unauthorized access; (3) search and common academic queries responding within 500 ms; (4) every Sprint ending with a working increment demonstrated in the Sprint Review; and (5) no critical defect open at release.

## Project Constraints

The project is an academic Agile exercise with limited time and team capacity. Institutional rules, data requirements and external-system integrations may change and should be validated before implementation.

## Expected Software Capabilities

Secure authentication, role-based access, student and course management, attendance management, marks and grade processing, notifications, and academic reporting.

## Stakeholder Alignment

The vision reflects the stakeholder needs identified in Unit 1: students need quick access to registration, attendance and results; faculty need efficient attendance and marks entry; administrators and examination staff need controlled records and reliable reports; and IT support needs a secure and maintainable system. The Product Owner represents these interests when prioritizing the Product Backlog.

# 3. Scrum Team Structure

| Role | Main Responsibility | Assigned To |
| --- | --- | --- |
| Product Owner | Defines requirements, prioritizes the Product Backlog, represents stakeholder interests and accepts completed work. | [Yadnesh Kshirsagar] |
| Scrum Master | Facilitates Scrum ceremonies, helps remove impediments and supports Agile practices. | [Yuvraj Jamdar] |
| Development Team | Designs, develops, tests, integrates and documents the application. | [Pratik Sakhare] |

# 4. Scrum Roles and Responsibilities

## Product Owner

Define and clarify requirements.

Maintain and prioritize the Product Backlog.

Represent stakeholder interests.

Review completed functionality.

Decide priorities using value, importance, dependencies and complexity.

## Scrum Master

Facilitate Sprint Planning, Daily Scrum, Sprint Review and Retrospective.

Help remove impediments.

Support team collaboration.

Keep Sprint work aligned with the Sprint Goal.

## Development Team

Design the application.

Implement User Stories.

Write and execute tests.

Integrate completed work.

Prepare documentation and demonstrations.

# 5. Epic Documentation

| Epic | Purpose | Main Features | Scope |
| --- | --- | --- | --- |
| Epic 1 – Student Management | Manage student records. | Registration, profile management, search, update, deletion. | Includes registration, profile view and update, search, update and removal of student records. Excludes admission and fee processing. |
| Epic 2 – Course Management | Maintain course information. | Add, update, assign students, view details. | Includes course creation, update, student assignment and course details. Excludes timetable scheduling. |
| Epic 3 – Attendance Management | Maintain attendance information. | Record attendance, view attendance, attendance reports. | Includes recording and viewing attendance and attendance reports. Excludes biometric or device-based capture. |
| Epic 4 – Marks and Academic Performance | Manage academic performance. | Enter marks, update marks, calculate grades, result sheets. | Includes marks entry and correction, grade calculation and result sheets. Excludes predictive performance analytics. |
| Epic 5 – Authentication and Security | Protect access to the platform. | Login, logout, password reset, role-based access control. | Includes login, logout, password reset and role-based access control. Excludes third-party single sign-on. |
| Epic 6 – Notifications | Communicate important academic events. | Attendance alerts, examination notifications, result notifications. | Includes attendance, examination and result notifications. Excludes third-party messaging gateways. |
| Epic 7 – Reporting | Provide academic and administrative reports. | Student, attendance, performance and course reports. | Includes student, attendance, performance and course reports. Excludes advanced analytics dashboards. |

# 6. User Story Repository

| ID | Epic | Role | User Story | SP |
| --- | --- | --- | --- | --- |
| US-01 | Authentication | Student | As a Student, I want to log in securely so that I can access my academic dashboard. | 8 |
| US-02 | Authentication | User | As a User, I want to log out so that my session is closed when I finish using the system. | 3 |
| US-03 | Authentication | User | As a User, I want to reset my password so that I can regain access when I forget my password. | 5 |
| US-04 | Student Management | Administrator | As an Administrator, I want to register a student so that a student has a complete institutional record. | 5 |
| US-05 | Student Management | Administrator | As an Administrator, I want to search for a student so that I can quickly find the required student record. | 3 |
| US-06 | Student Management | Administrator | As an Administrator, I want to update student information so that academic records remain current. | 3 |
| US-07 | Student Management | Administrator | As an Administrator, I want to remove a student record when permitted so that inactive or incorrect records can be handled appropriately. | 5 |
| US-08 | Course Management | Administrator | As an Administrator, I want to add a course so that the institution can maintain available courses. | 3 |
| US-09 | Course Management | Administrator | As an Administrator, I want to update course information so that course details remain current. | 3 |
| US-10 | Course Management | Administrator | As an Administrator, I want to assign students to courses so that course enrollment is recorded correctly. | 5 |
| US-11 | Course Management | Student | As a Student, I want to view course details so that I can understand the courses available to me. | 2 |
| US-12 | Attendance | Faculty Member | As a Faculty Member, I want to record student attendance so that attendance records remain accurate and updated. | 5 |
| US-13 | Attendance | Student | As a Student, I want to view my attendance so that I can monitor my attendance status. | 3 |
| US-14 | Attendance | Faculty Member | As a Faculty Member, I want to generate an attendance report so that I can review attendance for a course or period. | 5 |
| US-15 | Performance | Faculty Member | As a Faculty Member, I want to enter marks so that student academic performance is recorded. | 5 |
| US-16 | Performance | Faculty Member | As a Faculty Member, I want to update marks so that authorized corrections can be made. | 3 |
| US-17 | Performance | System | As the System, I want to calculate grades so that results follow the defined grading rules. | 5 |
| US-18 | Performance | Examination Staff | As an Examination Staff member, I want to generate result sheets so that official result information can be prepared. | 5 |
| US-19 | Notifications | Student | As a Student, I want to receive attendance alerts so that I am informed about important attendance conditions. | 5 |
| US-20 | Notifications | Student | As a Student, I want to receive examination notifications so that I know about important examination information. | 3 |
| US-21 | Notifications | Student | As a Student, I want to receive result notifications so that I know when results are available. | 3 |
| US-22 | Reporting | Administrator | As an Administrator, I want to generate a student report so that I can obtain required student information. | 5 |
| US-23 | Reporting | Administrator | As an Administrator, I want to generate an attendance report so that I can review attendance information in report form. | 3 |
| US-24 | Reporting | Administrator | As an Administrator, I want to generate a performance report so that I can review academic performance. | 5 |
| US-25 | Reporting | Administrator | As an Administrator, I want to generate a course report so that I can review course-related information. | 3 |
| US-26 | Authentication | Administrator | As an Administrator, I want to assign roles and permissions to users so that each user can access only the functions appropriate to their role. | 5 |
| US-27 | Student Management | Student | As a Student, I want to view my profile and update my permitted contact details so that my personal information stays accurate. | 3 |

# 7. Acceptance Criteria Document

Acceptance Criteria are the measurable conditions that must be true before a User Story is considered complete. They provide the clear definition of "Done" for each story in the User Story Repository.

## US-01 Student Login

The login page loads successfully.

Registered credentials are accepted.

Invalid credentials show an appropriate error message.

Successful login opens the dashboard appropriate to the user's role.

Users cannot access functions outside their assigned role.

## US-02 User Logout

A logged-in user can select the logout option.

The active session is terminated successfully.

After logout, protected pages cannot be accessed without logging in again.

## US-03 Password Reset

A registered user can start the password-reset process.

Required identity or verification information is validated.

A valid reset process allows the user to create a new password.

Invalid or unrecognized reset requests show an appropriate message.

## US-04 Register Student

An authorized administrator can open student registration.

Required fields are validated.

Valid data creates a student record.

Duplicate institutional identifiers are rejected.

The saved student can be found through search.

## US-05 Search Student

An authorized user can enter search criteria.

Matching student records are displayed.

No-match searches show a clear result.

Protected data is not exposed to unauthorized users.

## US-06 Update Student

An authorized administrator can open an existing student record.

Editable fields are validated.

Valid changes are saved successfully.

Updated information is visible when the record is viewed again.

## US-07 Remove Student

Only an authorized user can initiate student-record removal.

The system requests confirmation before removal.

A permitted record is removed or marked inactive according to the defined rule.

The record no longer appears as an active student after the operation.

## US-08 Add Course

An authorized user can open course creation.

Required course fields are validated.

A valid course is saved successfully.

The new course appears in course listings.

## US-09 Update Course

An authorized user can select an existing course.

Editable course fields are validated.

Valid changes are saved successfully.

Updated course information appears in subsequent views.

## US-10 Assign Students

An authorized user can select a course.

Eligible students can be selected.

The course assignment is saved.

Duplicate assignment is prevented.

## US-11 View Course Details

A student can view courses available to them.

Course details are displayed clearly.

Only courses appropriate to the student's access are shown.

## US-12 Record Attendance

Faculty can select an assigned course.

Faculty can select a lecture date.

Faculty can mark attendance for the relevant students.

Attendance records are saved successfully.

Saved attendance can be viewed afterward.

## US-13 View Attendance

A student can access attendance for enrolled courses.

Attendance is shown for the relevant course and period.

Displayed information matches the stored attendance records.

## US-14 Generate Attendance Report

Authorized faculty can select a course or period.

The system retrieves the relevant attendance records.

The report contains the required attendance information.

Only authorized information is included.

## US-15 Enter Marks

Authorized faculty can select a course and assessment.

Valid marks are accepted.

Invalid values are rejected.

Saved marks can be reviewed.

## US-16 Update Marks

Authorized faculty can select an existing mark record.

Updated values are validated.

Valid corrections are saved.

The revised mark is visible after saving.

## US-17 Calculate Grades

The configured grading rule is applied.

Grades are generated from valid marks.

Incomplete data does not produce an incorrect grade.

Calculated grades can be reviewed before publication where required.

## US-18 Generate Result Sheets

Authorized examination staff can select the required examination data.

Valid marks and calculated grades are included.

The result sheet contains the required fields.

Only authorized users can generate or access official result information.

## US-19 Attendance Alerts

The system identifies attendance conditions that meet the configured alert rule.

The relevant student receives the attendance alert.

The alert contains understandable information about the condition.

## US-20 Examination Notifications

Authorized examination information can trigger a notification.

The relevant students receive the notification.

The notification contains the important examination information.

## US-21 Result Notifications

A result publication event can trigger a notification.

The relevant students receive the notification.

The notification indicates that the result is available.

## US-22 Generate Student Report

An authorized administrator can select a report type.

Relevant student information is retrieved.

Required report fields are present.

Only authorized information is included.

## US-23 Generate Attendance Report

An authorized administrator can select the required attendance scope.

Relevant attendance records are retrieved.

The generated report contains the required attendance fields.

Only authorized information is included.

## US-24 Generate Performance Report

An authorized administrator can select the required performance scope.

Relevant marks and grades are retrieved.

The generated report contains the required performance information.

Only authorized information is included.

## US-25 Generate Course Report

An authorized administrator can select the course-report scope.

Relevant course information is retrieved.

The generated report contains the required course fields.

Only authorized information is included.

## US-26 Role-Based Access Control

An authorized administrator can assign a role to a user.

Each role has a defined set of permitted functions.

A user cannot open pages or perform actions outside the assigned role.

A change of role takes effect on the user's next login.

Unauthorized access attempts show an access-denied message.

## US-27 Student Profile Management

A logged-in student can open their own profile.

Profile information is displayed correctly.

Permitted contact details can be edited and are validated.

Fields that only administrators may change are read-only for students.

Saved changes are visible when the profile is viewed again.

# 8. Prioritized Product Backlog

The Product Backlog consolidates all 27 User Stories in priority order, based on business value, user importance, technical dependencies and implementation complexity.

| Priority | ID | Epic | User Story | SP |
| --- | --- | --- | --- | --- |
| High | US-01 | Authentication | As a Student, I want to log in securely so that I can access my academic dashboard. | 8 |
| High | US-04 | Student Management | As an Administrator, I want to register a student so that a student has a complete institutional record. | 5 |
| High | US-05 | Student Management | As an Administrator, I want to search for a student so that I can quickly find the required student record. | 3 |
| High | US-08 | Course Management | As an Administrator, I want to add a course so that the institution can maintain available courses. | 3 |
| High | US-10 | Course Management | As an Administrator, I want to assign students to courses so that course enrollment is recorded correctly. | 5 |
| High | US-12 | Attendance | As a Faculty Member, I want to record student attendance so that attendance records remain accurate and updated. | 5 |
| High | US-13 | Attendance | As a Student, I want to view my attendance so that I can monitor my attendance status. | 3 |
| High | US-15 | Performance | As a Faculty Member, I want to enter marks so that student academic performance is recorded. | 5 |
| High | US-17 | Performance | As the System, I want to calculate grades so that results follow the defined grading rules. | 5 |
| High | US-26 | Authentication | As an Administrator, I want to assign roles and permissions to users so that each user can access only the functions appropriate to their role. | 5 |
| Medium | US-02 | Authentication | As a User, I want to log out so that my session is closed when I finish using the system. | 3 |
| Medium | US-03 | Authentication | As a User, I want to reset my password so that I can regain access when I forget my password. | 5 |
| Medium | US-06 | Student Management | As an Administrator, I want to update student information so that academic records remain current. | 3 |
| Medium | US-09 | Course Management | As an Administrator, I want to update course information so that course details remain current. | 3 |
| Medium | US-11 | Course Management | As a Student, I want to view course details so that I can understand the courses available to me. | 2 |
| Medium | US-14 | Attendance | As a Faculty Member, I want to generate an attendance report so that I can review attendance for a course or period. | 5 |
| Medium | US-16 | Performance | As a Faculty Member, I want to update marks so that authorized corrections can be made. | 3 |
| Medium | US-18 | Performance | As an Examination Staff member, I want to generate result sheets so that official result information can be prepared. | 5 |
| Medium | US-22 | Reporting | As an Administrator, I want to generate a student report so that I can obtain required student information. | 5 |
| Medium | US-23 | Reporting | As an Administrator, I want to generate an attendance report so that I can review attendance information in report form. | 3 |
| Medium | US-24 | Reporting | As an Administrator, I want to generate a performance report so that I can review academic performance. | 5 |
| Medium | US-25 | Reporting | As an Administrator, I want to generate a course report so that I can review course-related information. | 3 |
| Medium | US-27 | Student Management | As a Student, I want to view my profile and update my permitted contact details so that my personal information stays accurate. | 3 |
| Low | US-07 | Student Management | As an Administrator, I want to remove a student record when permitted so that inactive or incorrect records can be handled appropriately. | 5 |
| Low | US-19 | Notifications | As a Student, I want to receive attendance alerts so that I am informed about important attendance conditions. | 5 |
| Low | US-20 | Notifications | As a Student, I want to receive examination notifications so that I know about important examination information. | 3 |
| Low | US-21 | Notifications | As a Student, I want to receive result notifications so that I know when results are available. | 3 |

Prioritization is based on business value, user importance, technical dependencies and implementation complexity. Authentication and core academic workflows are placed ahead of secondary enhancements. Some Medium-priority stories, such as logout and password reset, are scheduled early because they complete the authentication foundation that other stories depend on.

# 9. Story Point Estimation Sheet

| Points | Complexity |
| --- | --- |
| 1 | Very Easy |
| 2 | Easy |
| 3 | Moderate |
| 5 | Difficult |
| 8 | Very Difficult |
| 13 | Highly Complex |

| ID | Story | SP |
| --- | --- | --- |
| US-01 | As a Student, I want to log in securely | 8 |
| US-02 | As a User, I want to log out | 3 |
| US-03 | As a User, I want to reset my password | 5 |
| US-04 | As an Administrator, I want to register a student | 5 |
| US-05 | As an Administrator, I want to search for a student | 3 |
| US-06 | As an Administrator, I want to update student information | 3 |
| US-07 | As an Administrator, I want to remove a student record when permitted | 5 |
| US-08 | As an Administrator, I want to add a course | 3 |
| US-09 | As an Administrator, I want to update course information | 3 |
| US-10 | As an Administrator, I want to assign students to courses | 5 |
| US-11 | As a Student, I want to view course details | 2 |
| US-12 | As a Faculty Member, I want to record student attendance | 5 |
| US-13 | As a Student, I want to view my attendance | 3 |
| US-14 | As a Faculty Member, I want to generate an attendance report | 5 |
| US-15 | As a Faculty Member, I want to enter marks | 5 |
| US-16 | As a Faculty Member, I want to update marks | 3 |
| US-17 | As the System, I want to calculate grades | 5 |
| US-18 | As an Examination Staff member, I want to generate result sheets | 5 |
| US-19 | As a Student, I want to receive attendance alerts | 5 |
| US-20 | As a Student, I want to receive examination notifications | 3 |
| US-21 | As a Student, I want to receive result notifications | 3 |
| US-22 | As an Administrator, I want to generate a student report | 5 |
| US-23 | As an Administrator, I want to generate an attendance report | 3 |
| US-24 | As an Administrator, I want to generate a performance report | 5 |
| US-25 | As an Administrator, I want to generate a course report | 3 |
| US-26 | As an Administrator, I want to assign roles and permissions to users | 5 |
| US-27 | As a Student, I want to view my profile and update my permitted contact details | 3 |

Story Points represent relative effort and complexity rather than hours. Planning Poker can be used to reach team agreement and revise estimates when understanding changes.

## Planning Poker Session (Simulated)

The team estimated stories with Planning Poker. Each developer privately selected a card, the cards were revealed together, and differences were discussed before a new vote. For example, US-01 moved from 5 to 8 after the team agreed that secure session handling adds complexity, and US-17 settled at 5 once the grading rule was clarified.

| Story | Developer 1 | Developer 2 | Developer 3 | Agreed SP |
| --- | --- | --- | --- | --- |
| US-01 Student Login | 5 | 8 | 8 | 8 |
| US-02 User Logout | 2 | 3 | 3 | 3 |
| US-11 View Course Details | 2 | 2 | 3 | 2 |
| US-17 Calculate Grades | 3 | 5 | 8 | 5 |
| US-26 Role-Based Access Control | 5 | 5 | 8 | 5 |

# 10. Sprint Planning Document

Each Sprint is a one-week timebox of six working days. Sprint 1 carries 21 Story Points, and later Sprints take on more work as the team gains familiarity with the product and its tools. Each Sprint produces a working, demonstrable increment.

## Sprint 1

Sprint Goal: Establish the project foundation and secure access.

Stories: US-01, US-02, US-04, US-26

Expected outcome: Login, logout, role-based access control and student registration.

Total Story Points: 21

## Sprint 2

Sprint Goal: Complete student management and core course management.

Stories: US-03, US-05, US-06, US-07, US-08, US-09, US-10, US-27

Expected outcome: Password reset, student search, update, removal and profile management, and course creation, update and assignment.

Total Story Points: 30

## Sprint 3

Sprint Goal: Deliver course details, attendance and academic performance.

Stories: US-11, US-12, US-13, US-14, US-15, US-16, US-17

Expected outcome: Course details, attendance, marks and grade calculation.

Total Story Points: 28

## Sprint 4

Sprint Goal: Complete results, notifications and reporting.

Stories: US-18, US-19, US-20, US-21, US-22, US-23, US-24, US-25

Expected outcome: Result sheets, notifications and reports.

Total Story Points: 32

## Sprint Planning Meeting (Simulated)

For Sprint 1 the Product Owner presented the highest-priority stories. The team confirmed their Acceptance Criteria, estimated each story using Planning Poker, selected US-01, US-02, US-04 and US-26 (21 Story Points) and agreed the Sprint Goal: "Establish the project foundation and secure access."

## Daily Scrum Sample (Sprint 1, Day 3)

Each member answers three questions: What did I complete yesterday? What will I do today? What challenges am I facing?

| Team Member | Completed Yesterday | Plan for Today | Challenges |
| --- | --- | --- | --- |
| Developer 1 (Backend) | Created the user and role tables. | Implement login validation and session handling. | Waiting for the final role list. |
| Developer 2 (Frontend) | Designed the login and dashboard screens. | Connect the login screen to the backend. | Dashboard layout differs by role. |
| Developer 3 (Testing and documentation) | Wrote acceptance test cases for US-01. | Test registration form validation (US-04). | Test data for duplicate identifiers is incomplete. |

# 11. Sprint Backlog

| Sprint | Backlog Items | Primary Work | Story Points |
| --- | --- | --- | --- |
| Sprint 1 | US-01, US-02, US-04, US-26 | Project setup, authentication, role-based access control and student registration. | 21 |
| Sprint 2 | US-03, US-05, US-06, US-07, US-08, US-09, US-10, US-27 | Password reset, student management and course management. | 30 |
| Sprint 3 | US-11, US-12, US-13, US-14, US-15, US-16, US-17 | Course details, attendance and performance. | 28 |
| Sprint 4 | US-18, US-19, US-20, US-21, US-22, US-23, US-24, US-25 | Results, notifications and reporting. | 32 |

# 12. Scrum Board

| Backlog | To Do | In Progress | Testing | Completed |
| --- | --- | --- | --- | --- |
| US-03 Password Reset | US-26 Role-Based Access Control | US-01 Student Login | US-04 Register Student | Project Setup |
| US-05 Search Student | — | — | — | US-02 User Logout |
| US-06 Update Student | — | — | — | — |
| US-12 Record Attendance | — | — | — | — |

This board is a mid-Sprint 1 snapshot. The Sprint 1 stories are spread across the working columns, and the Backlog column holds the next candidate stories for later Sprints. During Sprint execution, stories move between columns as work progresses and satisfies the Definition of Done.

# 13. Burndown Chart

The burndown below tracks Sprint 1, whose stories (US-01, US-02, US-04 and US-26) total 21 Story Points over a six-day Sprint. The planned line shows the ideal rate of progress; the actual line is a simulated record of remaining effort at the end of each working day. During real Sprint execution the actual value is updated daily after the Daily Scrum.

| Sprint Day | Planned Remaining Story Points | Actual Remaining Story Points (simulated) |
| --- | --- | --- |
| Day 1 | 21 | 21 |
| Day 2 | 17 | 18 |
| Day 3 | 13 | 14 |
| Day 4 | 9 | 10 |
| Day 5 | 4 | 5 |
| Day 6 | 0 | 0 |

# 14. Sprint Review Report

The Sprint Review is used to demonstrate completed functionality to stakeholders and collect feedback. Accepted work remains completed, while requested changes become new or revised Product Backlog items.

## Sprint 1 Review Summary (Simulated)

Sprint 1 Goal: Establish the project foundation and secure access. Completed: 21 of 21 Story Points. Stories were demonstrated to the Product Owner and stakeholders.

| Story | Result | Feedback / Follow-up |
| --- | --- | --- |
| US-01 Student Login | Accepted | Add a visible show/hide option for the password field. |
| US-02 User Logout | Accepted | No change requested. |
| US-04 Register Student | Accepted with change | Add department and program fields; added to the Product Backlog. |
| US-26 Role-Based Access Control | Accepted | Review the role list with the Product Owner before Sprint 2. |

## Review Areas Across Sprints

| Area | Demonstration | Feedback to Capture |
| --- | --- | --- |
| Authentication | Login, logout and access behavior. | Ease of use and access issues. |
| Student Management | Registration, search and update. | Required fields and workflow clarity. |
| Course Management | Course creation and assignment. | Course rules and assignment behavior. |
| Attendance | Attendance entry and student view. | Visibility and usability. |
| Performance | Marks and grade calculation. | Validation and result clarity. |
| Reporting | Generated reports. | Required fields and usefulness. |

# 15. Sprint Retrospective Report

| Area | Observation | Improvement |
| --- | --- | --- |
| What went well | Small User Stories made work easier to plan. | Continue using focused stories. |
| What went well | Acceptance criteria created a shared definition of completion. | Write criteria before implementation. |
| Challenge | Dependencies between authentication, student data and modules can delay work. | Identify dependencies during Sprint Planning. |
| Challenge | Additional ideas can increase scope. | Move new ideas to the Product Backlog. |
| Improvement | Testing can be left too late. | Treat testing as part of each User Story. |

# 16. Agile Framework Comparison Report

| Framework | Characteristics | Suitability |
| --- | --- | --- |
| Scrum | Sprints, Product Backlog, defined roles and regular reviews/retrospectives. | High – matches the project structure and academic exercise. |
| Kanban | Continuous flow and visual work management with work-in-progress limits. | Medium – useful for ongoing support but less structured for this exercise. |
| Extreme Programming (XP) | Strong engineering practices, frequent feedback and testing. | Medium-High – useful as a complementary technical practice. |
| Lean Development | Value focus, waste reduction and fast learning. | Medium – useful as a guiding mindset. |
| LeSS | Scaling Scrum across multiple teams. | Low – unnecessary for a small academic team. |
| SAFe | Structured scaling across large organizations. | Low – too much coordination overhead for this project. |
| Scrum@Scale | Coordinates multiple Scrum teams. | Low – more appropriate when the product has several Scrum teams. |

## Recommended Framework

Scrum is the most suitable primary framework because the project is explicitly organized around Epics, User Stories, Story Points, Product Backlog management, Sprint Planning, Scrum Boards and Scrum ceremonies. XP practices can complement Scrum where stronger engineering practices are needed. With a single small team, a fixed scope of 27 User Stories and 111 Story Points, and four short Sprints, the project does not need a scaling framework such as LeSS, SAFe or Scrum@Scale.

# 17. Project Timeline and Release Roadmap

| Phase | Focus | Main Deliverables | Timeline |
| --- | --- | --- | --- |
| Release 0 | Agile setup | Vision, Scrum roles, Epics, initial backlog and estimates. | Before Week 1 |
| Sprint 1 | Authentication and registration | Login/logout, role-based access control and student registration. | Week 1 |
| Sprint 2 | Student and course management | Password reset, student management and course workflows. | Week 2 |
| Sprint 3 | Attendance and performance | Course details, attendance, marks and grade calculation. | Week 3 |
| Sprint 4 | Results, notifications and reporting | Result sheets, notifications and reports. | Week 4 |
| Future Release | Enhancement | Additional analytics, integrations and improvements based on feedback. | After Week 4 |

The planned dependency flow is Authentication → Student Records → Course Assignment → Attendance → Marks and Grades → Results → Reporting and Notifications. The Product Owner may adjust the order when technical or business information changes.

# 18. Complete Agile Documentation Summary

| Required Deliverable | Section |
| --- | --- |
| Agile Project Planning Report | 1 |
| Product Vision Document | 2 |
| Scrum Team Structure | 3 |
| Scrum Roles and Responsibilities Document | 4 |
| Epic Documentation | 5 |
| User Story Repository | 6 |
| Acceptance Criteria Document | 7 |
| Prioritized Product Backlog | 8 |
| Story Point Estimation Sheet | 9 |
| Sprint Planning Document | 10 |
| Sprint Backlog | 11 |
| Scrum Board | 12 |
| Burndown Chart | 13 |
| Sprint Review Report | 14 |
| Sprint Retrospective Report | 15 |
| Agile Framework Comparison Report | 16 |
| Project Timeline and Release Roadmap | 17 |
| Complete Agile Documentation | 18 |

This document brings together the Unit 2 Agile planning deliverables into one coherent submission. The flow from Epics to User Stories, acceptance criteria, prioritization, estimates and Sprint planning is kept consistent so that the Agile plan can be followed during development.